## Sheet1
Time Estimation Document
Project Name: Visual Live
Sr. No. | Task | Understanding/ Queries if Any | Estimated Hours
1 | Add Model endpoints specific to project. Make sure it only show project models, not user. a) GET list b) GET single model c) PATCH model details d) POST upload model e) DELETE model Also, remove project models from user endpoint for models. Right now the api/v1/model_files and api/v2/model_files is including project models. These endpoints should only show user models. We need separate endpoints for project models. | Will integrate the apis GET list, GET single model, PATCH model details, POST upload model and DELETE model for project models only. And Will also remove the project models from user endpoints for model | 5
2 | Bounds API Add a way to update existing Bounds on Section: a) PATCH /api/v2/sections/{section-id}/bounds (Prefered) b) If using PATCH and Bounds doesn’t exist, then it should create a new Bounds. | Will integrate the patch(update) api for bounds on section. Will integrate api to create the new bound if the bound for the section don’t exist. | 3
3 | Workset API a) DELETE {{baseUrl}}/api/v2/sets/{set-id} b) DELETE {{baseUrl}}/api/v2/sections/{section-id} c) DELETE {{baseUrl}}/api/v2/bounds/{bounds-id} d) DELETE {{baseUrl}}/api/v2/worksets/{workset-id} | Will integrate workset api for delete set, section, bound and workset. | 4
4 | POST Items for Sets and Sections a) POST api/v2/model_files/{model-id}/sets/{set-id}/items b) POST api/v2/model_files/{model-id}/sections/{set-id}/items When adding items to a Set or Section, we need to be able to upload multiple items via JSON. Right now I can only add one at a time. It should not create an Item if there is already an Item with the same GUID. | Will integrate the apis to post the items in the set and section. The items can able to create more than one item at a time and GUID fileld should be unique for the item. | 4
5 | Improve Navigation when updating details, user permissions, uploading model, etc Adding or editing a user Adding or editing a location Editing Project Details Uploading Thumbnail | Will improve the navigation for updating details, user permissions and uploading models. | 10
6 | Print Markers for Locations (halfway implemented) Print button for each location Print all at the top of location page Marker formatting with QR code Image should be 4.25 in x 5.5 in when printed QR code has model UUID + marker number (ex. “78777879 1”) | Will add print button for each location and print all button at the top of location page. Please provide more details about marker formatting with QR code | 6
|  | Total Hours | 32
Please Note | Estimates may change during the process of development.